## Sheet1
Probability of Occurrence
Very Unlikely | 1
Somewhat unlikely | 3
50-50 possibility | 5
Somewhat likely | 7 | [6 empty] | Heat Map Before Risk Mitigation
Very likely | 9
[7 empty] | 9 | [6 empty] | Risks | RS | I*P
[7 empty] | 7 |  |  |  |  | R1 |  | R1 - Software Integration failure | 56 | 8*7
[6 empty] | Likelihood | 5 | [6 empty] | R2 - Object detection failure | 27 | 9*3
Impact of Risk |  | Costs | Schedule | Scope | Quality |  | 3 |  | R3 |  |  |  | R2 | R3 - Extensive research | 6 | 2*3
Very Low | 1 | 0 - $99,999 | 0 - 7 | Scope impact barely discernable | Minor defects in production |  | 1
Somewhat Low | 2 | $100,000 - $199,999 | 8 to 14 | Minor areas of scope impaired | Small number of moderate defects in prod |  | 0 | 1 | 2 | 4 | 6 | 8 | 9
Moderate | 4 | $200,000 - $299,999 | 15 to 21 | Many minor areas of scope impaired | Moderate number of moderate defects in prod |  |  |  |  | Impact
Somewhat High | 6 | $300,000 - $399,999 | 22 to 28 | Major areas of scope impaired | High number of moderate defects in prod
High | 8 | $400,000 - $499,999 | 29 to 34 | Scope reduction unacceptable | Major defects in prod |  |  | Updated Heat Map
Extremely High | 9 | $500,000 + | 35 days + | Final product undeliverable or useless | Final product is inoperable
[7 empty] | 9 | [6 empty] | Risks | RS | I*P
[7 empty] | 7 | [6 empty] | R1 - Software Integration failure | 30 | 6*5
lmpact X Probabilty = RS | [5 empty] | Likelihood | 5 |  |  | R3 | R1 |  |  | R2 - Object detection failure | 12 | 4*3
lmpact X Probabilty = RS |  | ` |  |  |  |  | 3 |  |  | R2 |  |  |  | R3 - Extensive research | 20 | 4*5
Thresholds | [6 empty] | 1
High: 45 - 81 | [6 empty] | 0 | 1 | 2 | 4 | 6 | 8 | 9
Medium: 13 - 44
Low: 0 - 12
Impact